## Updated Time Schedule
Project title: |  | Modernizacion and equipment of the Basic Art School Bystré | [9 empty] | srpen 2009
Expected start date:
Activity |  | Indicative Disbursement (EUR) | [10 empty] | Total
|  |  | 1.Q 2009 | 2.Q 2009 | 3.Q 2009 | 4.Q 2009 | 1.Q 2010 | 2.Q 2010 | 3.Q2010 | 4.Q2010 | 1.Q2011 | 2.Q2011
Renovation of the school (including cellar, 1st floor, 2nd floor, 3rd floor and new entrance)
Activity 1 | 1.PP - stavební část |  | 0 | 0 | 690505.83 | 200864.86 | 78736.35 | 98271.39 | 70674.1 | 0 | 0 |  | 1139052.53
| 3.NP - stavební část |  | 0 | 0 | 0 | 0 | 1144916.85 | 1230819.38 | 0 | 0 | 0 |  | 2375737.23
| 1.NP+2.NP - stavební část - exteriér budovy |  | 0 | 0 | 0 | 0 | 0 | 0 | 2324863.73 | 0 | 0 |  | 2324864.73
| 1.NP - stavební část |  | 0 | 0 | 0 | 0 | 0 | 0 | 281631.35 | 0 | 0 |  | 281630.35
| 2.NP - stavební část |  | 0 | 0 | 245623.14 | 0 | 0 | 0 | 0 | 0 | 0 |  | 245623.14
| činnosti související s realizací |  | 0 | 0 | 14994 | 6664 | 6664 | 6664 | 27685.35 | 0 | 0 |  | 62671.35
| Total per quarter |  | 0 | 0 | 951122.97 | 207529.86 | 1230317.2 | 1335754.77 | 2704854.53 | 0 | 0 | 0 | 6429579.33
| Total per year |  |  |  |  | 1158652.83 |  |  |  | 5270926.5 |  | 0 | 6429579.33
Purchase of equipment and furnishins
Activity 2 | 1.PP - vybavení |  | 0 | 0 | 19873 | 0 | 0 | 0 | 82586 | 0 | 0 |  | 102459
| 3.NP - vybavení |  | 0 | 0 | 0 | 0 | 0 | 1048222.21 |  | 0 | 0 |  | 1048222.21
| 1.NP+2.NP - vybavení |  | 0 | 0 | 0 | 0 | 0 | 0 | 164220 | 0 | 0 |  | 164220
| 1.NP - vybavení |  | 0 | 0 | 0 | 0 | 0 | 0 | 894716.97 | 0 | 0 |  | 894716.97
| 2.NP - vybavení |  | 0 | 0 | 595000 | 232430.8 | 0 | 0 | 0 | 0 | 0 |  | 827430.8
| Total per quarter |  | 0 | 0 | 614873 | 232430.8 | 0 | 1048222.21 | 1141522.97 | 0 | 0 | 0 | 3037048.98
| Total per year |  |  |  |  | 847303.8 |  |  |  | 2189745.18 |  | 0 | 3037048.98
Project manatement and publicity (including public procurement)
Activity 3 | Služby - zpracování VŘ (zvýšená cena) |  | 0 | 0 | 19000 | 25000 | 0 | 9000 | 0 | 0 | 0 |  | 53000
| Služby - právník (zrušeno) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Služby - podklady VŘ (upraveno) |  | 0 | 0 | 54000 |  | 0 | 0 | 6000 | 0 | 0 |  | 60000
| Služby - prováděcí PD (upraveno) |  |  | 0 | 98880 | 0 | 0 | 0 | 0 | 24720 | 0 |  | 123600
| Služby - AD (upraveno) |  |  | 0 | 6520 | 9870 | 9870 | 9870 | 9870 | 11500 | 0 |  | 57500
| Služby - TDI (upraveno) |  |  | 0 | 10880 | 16320 | 16320 | 16320 | 16320 | 19040 | 0 |  | 95200
| Managmant - překladatel (upraveno) |  | 0 | 0 | 2250 | 6750 | 6750 | 6750 | 6750 | 4500 | 0 |  | 33750
| Managmant - monitoring (upraveno) |  |  | 0 | 2500 | 7500 | 7500 | 7500 | 7500 | 5000 | 0 |  | 37500
| Publicita |  | 0 | 0 | 11900 | 0 | 0 | 0 | 47541 | 0 | 0 |  | 59441
| Total per quarter |  | 0 | 0 | 205930 | 65440 | 40440 | 49440 | 93981 | 64760 | 0 | 0 | 519991
| Total per year |  |  |  |  | 271370 |  |  |  | 248621 |  | 0 | 519991
Total cost per year | [5 empty] | 2277326.63 |  |  |  | 7709292.68 |  | 0 | 9986619.31
Návod na vyplnění tabulky:
Tato tabulka slouží jako podklad pro vyplnění Plánu implementace projektu (PIP). PIP bude součástí Dohody o udělení grantu a bude sloužit pro monitorování realizace projektu. Vyplňujte, prosím, v angličtině.
V tabulce uvádějte aktualizované časové údaje. Aktivity uvedené v žádosti o projekt sdružte do maximálně 4 aktivit, které mohou sdružovat větší počet sub-aktivit. Počátek realizace projektu stanovte nejdříve ode dne oprávněnosti výdajů projektu (viz.Grant Offer Letter). Maximální délka projektu je také stanovena v Grant Offer Letter. Odhadněte výdaje projektu po kalendářních čtvrtletích. Vpisujte oprávněné výdaje včetně kofinancování.