## Updated Time Schedule
Project title: |  | Modernization and equipment of the Basic Art School Bystré
Expected start date: |  | 2009-02-01
Activity |  | Indicative Disbursement (EUR) | [10 empty] | Total
|  |  | 1.Q 2009 | 2.Q 2009 | 3.Q 2009 | 4.Q 2009 | 1.Q 2010 | 2.Q 2010 | 3.Q2010 | 4.Q2010 | 1.Q2011 | 2.Q2011
Renovation of the school (including cellar, 1st floor, 2nd floor, 3rd floor and new entrance)
Activity 1 | sublevel - constructional part |  | 0 | 0 | 1270 | 5933 | 7314 | 6170 | 6976 | 3712 | 0 |  | 31375
| 3rd floor - constructional part |  | 0 | 0 | 9368 | 9421 | 17440 | 13354 | 11682 | 26999 | 0 |  | 88264
| 1.st +2nd fl. - constr. part - exterior of the building |  | 0 | 0 | 9215 | 10595 | 9661 | 9552 | 5920 | 15774 | 0 |  | 60717
| 1st floor - constructional part |  | 0 | 0 | 0 | 0 | 0 | 3412 | 6993 | 0 | 0 |  | 10405
| 2nd floor - constructional part |  | 0 | 0 | 5611 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5611
| Total per quarter |  | 0 | 0 | 25464 | 25949 | 34415 | 32488 | 31571 | 46485 | 0 | 0 | 196372
| Total per year |  |  |  |  | 51413 |  |  |  | 144959 |  | 0 | 196372
Purchase of equipment and furnishings
Activity 2 | sublevel - equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4752 | 0 |  | 4752
| 3rd floor - equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34390 | 0 |  | 34390
| 1.st +2nd fl.- equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 5372 | 0 | 0 |  | 5372
| 1st floor - equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 33590 | 0 | 0 |  | 33590
| 2nd floor - equipment |  | 0 | 0 | 31315 | 0 | 0 | 0 | 0 | 0 | 0 |  | 31315
| Total per quarter |  | 0 | 0 | 31315 | 0 | 0 | 0 | 38962 | 39142 | 0 | 0 | 109419
| Total per year |  |  |  |  | 31315 |  |  |  | 78104 |  | 0 | 109419
Project management and publicity (including public procurement)
Activity 3 | Services - working up of the selection procedure (higher price) |  | 0 | 681 | 0 | 1004 | 0 | 0 | 0 | 0 | 0 |  | 1685
| Services - lawyer (lower price) |  |  | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 0 |  | 278
| Services - translation - selection procedure |  | 0 | 2202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2202
| Services - implementary project documentation |  |  | 3670 | 152 | 152 | 152 | 152 | 152 | 157 | 0 |  | 4587
| Services – author supervision |  |  | 0 | 354 | 354 | 354 | 354 | 354 | 380 | 0 |  | 2150
| Services – engineering investor´s supervision |  |  | 0 | 612 | 612 | 612 | 612 | 612 | 626 | 0 |  | 3686
| Management - translator |  | 0 | 0 | 215 | 215 | 215 | 215 | 215 | 205 | 0 |  | 1280
| Management - monitoring |  |  | 0 | 640 | 640 | 640 | 640 | 640 | 640 | 0 |  | 3840
| Publicity |  | 0 | 0 | 359 | 0 | 0 | 0 | 0 | 1772 | 0 |  | 2131
| Total per quarter |  | 0 | 6553 | 2610 | 2977 | 1973 | 1973 | 1973 | 3780 | 0 | 0 | 21839
| Total per year |  |  |  |  | 12140 |  |  |  | 9699 |  | 0 | 21839
Total cost per year | [5 empty] | 94868 |  |  |  | 232762 |  | 0 | 327630
Návod na vyplnění tabulky:
Tato tabulka slouží jako podklad pro vyplnění Plánu implementace projektu (PIP). PIP bude součástí Dohody o udělení grantu a bude sloužit pro monitorování realizace projektu. Vyplňujte, prosím, v angličtině.
V tabulce uvádějte aktualizované časové údaje. Aktivity uvedené v žádosti o projekt sdružte do maximálně 4 aktivit, které mohou sdružovat větší počet sub-aktivit. Počátek realizace projektu stanovte nejdříve ode dne oprávněnosti výdajů projektu (viz.Grant Offer Letter). Maximální délka projektu je také stanovena v Grant Offer Letter. Odhadněte výdaje projektu po kalendářních čtvrtletích. Vpisujte oprávněné výdaje včetně kofinancování.